## Control Sheet
This draft is a working plan based on information available to MHHSP at the time of drafting. It has not been approved by Ofgem. It is an imperative to challenge and validate all assumptions in the draft with the aim of securing the earliest possible robust implementation date. The plan review process is designed to arrive at a credible, robust, and achievable plan that sees MHHS implemented as early as possible and preferably no later than the date set out in the existing Transition Timetable, which all programme parties are currently required to operate in accordance with. The programme looks forward to working with parties to challenge and identify opportunities to shorten the overall timelines in this plan in order to secure a swift introduction of MHHS and to allow the generation of the benefits that MHHS will bring, in particular for customers and in supporting broader activity to drive towards net zero.
MHHS-DEL546 Programme Milestone Register
The purpose of this document is to provide a register of the activities in the Programme Re-plan that have been assigned a milestone status and therefore, will be reported against and managed via programme governance.
Document Classification: | Public
Version Control
Version | Prepared by | Publication / Baseline Date | Comment
v0.1 | Joe Deal | 2022-07-29 | Drafted for first round of industry consultation
v1.0 | Joe Deal | 2022-08-01 | Published for first round of industry consultation

## Milestone Register Guidance
MHHS Programme Milestone Register Guidance |  |  | This draft is a working plan based on information available to MHHSP at the time of drafting. It has not been approved by Ofgem. It is an imperative to challenge and validate all assumptions in the draft with the aim of securing the earliest possible robust implementation date. The plan review process is designed to arrive at a credible, robust, and achievable plan that sees MHHS implemented as early as possible and preferably no later than the date set out in the existing Transition Timetable, which all programme parties are currently required to operate in accordance with. The programme looks forward to working with parties to challenge and identify opportunities to shorten the overall timelines in this plan in order to secure a swift introduction of MHHS and to allow the generation of the benefits that MHHS will bring, in particular for customers and in supporting broader activity to drive towards net zero.
How to read this document
This page provides an explanation of how to interpret the information in the Milestone Register tab
Milestone Register fields
Milestone Tier | Milestone ID | Milestone Title | Milestone Description | Programme Phase for Milestone approval | Workstream | Milestone Date | Critical Path | Critical Thread | Dependent on | Artefact required for milestone approval | Decision-making authority (governance group) | Party responsible for reporting RAG | Party applicability RACI
The tier of the milestone, denoting the activities' Critical Path / Thread relevance and programme governance level responsible for reporting and decision-making. Detail of Milestone Tier Classifications documented below. | Milestone unique identifier | Title of the milestone | Narrative description of the milestone | Phase of the programme that the milestone is due to be approved in | Associated programme workstream to identify the area of the programme that the milestone is most relevant for. This corresponds to the second 2 characters in the Milestone ID naming convention (T1-XX-XXXX) | Proposed date for milestone approval at the relevant programme goverance forum | If 'Yes', the milestone is considered to be on the programme's critical path to Go-Live | References the relevant Tier 1 dependent milestone | The unique milestone identifier of the predecessor milestone(s) | The associated artefact(s) that are required to support the completion of the milestone | Programme governance forum responsible for reporting on milestone progress and deciding on milestone changes / approval | Organisation responsible for reporting the RAG status of the milestone via the Milestone Status Report and relevant governance group | RACI to identify the applicability of milestones to different organisations engaged in the MHHS programme.
Milestone Tier Classifications
Milestone Tier | Milestone Tier Description | Milestone Tier Reference | Governance reporting, decision-making and change control
Tier 1 | Milestones that sit on the critical path for Go-Live and / or are under the purview of the Programme Steering Group. This includes milestones for the decision point associated with progressing to the next phase of the programme (i.e. Control Points). Tier 1 milestones are comprised of a number of sub-milestones (Tier 2 and 3) focused on activities and deliverables which will be key inputs into decision-making. | T1-XX-XXXX | Programme Steering Group (PSG)
Tier 2 | Milestones that sit on a critical thread and therefore, are direct dependencies for the delivery of critical path milestones. This includes commencement and completion checkpoints for key stages of activity, such as the stages of SIT. Tier 2 milestones are key input activities or deliverables for Tier 1 milestone decision points. | T2-XX-XXXX | Advisory Groups
Tier 3 | Milestones that are considered key input activities to Tier 2 (Critical Thread) milestones. This includes the approval of key artefacts and the release of test stubs required for a particular stage of PP testing. Working Groups and Sub-groups will be tasked with completing these tasks and reporting progress and completion to the appropriate Advisory Group to inform a decision. | T3-XX-XXXX | Advisory Groups
Milestone ID Convention |  |  | Example
TX-XX-XXXX |  |  | T1_CP_2000
TX | XX | XXXX | T1 | CP | 2000
Milestone Tier (See Milestone Tier Classifications above) | Programme Workstream | Numerical identifier | Milestone Tier (See Milestone Tier Classifications above) | Programme Workstream | Numerical identifier
T1 = Tier 1 | BC = Business Change | Free text to identify the sequencing of activities within the relevant workstream | Tier 1 | Control Point | This is the second Control Point in a series of six across the full duration of the programme
T2 = Tier 2 | CP = Control Point
T3 = Tier 3 | DB = Design & Build
EC = Engagement & Comms
MT = Migration & Transition
PM = Programme Management
RA = Readiness Assessment
RE = Regulatory
TE = Testing

## Milestone Register
This draft is a working plan based on information available to MHHSP at the time of drafting. It has not been approved by Ofgem. It is an imperative to challenge and validate all assumptions in the draft with the aim of securing the earliest possible robust implementation date. The plan review process is designed to arrive at a credible, robust, and achievable plan that sees MHHS implemented as early as possible and preferably no later than the date set out in the existing Transition Timetable, which all programme parties are currently required to operate in accordance with. The programme looks forward to working with parties to challenge and identify opportunities to shorten the overall timelines in this plan in order to secure a swift introduction of MHHS and to allow the generation of the benefits that MHHS will bring, in particular for customers and in supporting broader activity to drive towards net zero.
Milestone Tier | Milestone ID | Milestone Title | Milestone Description | Programme Phase for Milestone approval | Workstream | Milestone Date | Critical Path | Critical Thread | Dependent on | Artefact required for milestone approval | Decision-making authority (governance group) | Party responsible for reporting RAG | Party applicability RACI
T3 | T3_DE_0005 | Migration Design approved | - | System Design & Build | DE | - | - | - | - | - | DAG | SRO Design | -
T1 | T1_PM_1000 | Programme re-plan baselined (M5+) | - | System Design & Build | PM | - | Yes | - | - | Re-baselined Programme Plan POAP+ and key related RAID items Milestone Register | PSG | PMO | -
T3 | T3_MT_0005 | Migration, Cutover & Data Strategy approved | - | System Design & Build | MT | - | - | - | - | Migration, Cutover & Data Strategy | TMAG | SI Test | -
T3 | T3_TE_0015 | Test Data Overarching Approach & Plan approved | - | System Design & Build | TE | - | - | - | - | Test Data Overarching Approach & Plan | TMAG | SI Test | -
T3 | T3_PM_XXXX | PP impact assessment, planning and software/service procurement complete | - | System Design & Build | PM | - | - | - | T1_PM_1000 | - | - | - | -
T2 | T2_TE_0005 | Confirmation of SIT PPs | - | System Design & Build | TE | - | - | T1_TE_1000 SIT start (M9) | - | - | TMAG | SI Test | -
T3 | T3_TE_0010 | DIP Simulator released | - | System Design & Build | TE | - | - | - | - | - | TMAG | SI DevOps | -
T3 | T3_TE_0020 | Qualification Testing Approach & Plan approved | - | System Design & Build | TE | - | - | - | - | Qualification Testing Approach & Plan | TMAG | SI Test | -
T2 | T2_RE_0005 | Code and subsidiary document drafting for Data Services (BSC) approved | - | System Design & Build | RE | - | - | T1_RE_1000 Code changes baselined (M6) | - | - | CCAG | SRO Design, Code Bodies | -
T2 | T2_RE_0010 | Code and subsidiary document drafting for Metering (REC) approved | - | System Design & Build | RE | - | - | T1_RE_1000 Code changes baselined (M6) | - | - | CCAG | SRO Design, Code Bodies | -
T3 | T3_TE_0025 | Configuration & Release Management Approach & Plan approved | - | System Design & Build | TE | - | - | - | - | - | TMAG | SRO Design, Code Bodies | -
T2 | T2_RE_0015 | Code and subsidiary document drafting for BSC Central Services (BSC) approved | - | System Design & Build | RE | - | - | T1_RE_1000 Code changes baselined (M6) | - | - | CCAG | SRO Design, Code Bodies | -
T2 | T2_RE_0020 | Code and subsidiary document drafting for Registration (BSC & REC) approved | - | System Design & Build | RE | - | - | T1_RE_1000 Code changes baselined (M6) | - | - | CCAG | SRO Design, Code Bodies | -
T3 | T3_TE_0030 | SIT Component Integration Approach & Plan approved | - | System Design & Build | TE | - | - | - | - | SIT Component Integration Approach & Plan | TMAG | SI Test | -
T3 | T3_TE_0035 | SIT Functional Approach & Plan approved | - | System Design & Build | TE | - | - | - | - | SIT Functional Approach & Plan | TMAG | SI Test | -
T3 | T3_MT_0010 | Migration Entry Criteria approved | - | System Design & Build | MT | - | - | - | - | Migration Entry Criteria | TMAG | SI Test | -
T3 | T3_TE_0040 | Data Generator released | - | System Design & Build | TE | - | - | - | - | - | TMAG | SI DevOps | -
T2 | T2_RE_0030 | Code and subsidiary document drafting for Qualification (all codes) approved | - | System Design & Build | RE | - | - | T1_RE_1000 Code changes baselined (M6) | T3_TE_0020 | - | CCAG | SRO Design, Code Bodies | -
T2 | T2_RE_0025 | Code and subsidiary document drafting for Governance (BSC & REC) approved | - | System Design & Build | RE | - | - | T1_RE_1000 Code changes baselined (M6) | - | - | CCAG | SRO Design, Code Bodies | -
T2 | T2_RE_0035 | Code and subsidiary document drafting for Interfaces / Data Specification (REC) approved | - | System Design & Build | RE | - | - | T1_RE_1000 Code changes baselined (M6) | - | - | CCAG | SRO Design, Code Bodies | -
T2 | T2_RE_0040 | Code and subsidiary document drafting for Transition Text (all codes) approved | - | System Design & Build | RE | - | - | T1_RE_1000 Code changes baselined (M6) | T3_MT_0005, T3_DE_0005 | - | CCAG | SRO Design, Code Bodies | -
T2 | T2_RE_0045 | Code and subsidiary document drafting for Final Code mop-up (all codes) approved | - | System Design & Build | RE | - | - | T1_RE_1000 Code changes baselined (M6) | - | - | CCAG | SRO Design, Code Bodies | -
T3 | T3_TE_0045 | SIT Non-Functional Approach & Plan approved | - | System Design & Build | TE | - | - | - | - | SIT Non-Functional Approach & Plan | TMAG | SI Test | -
T3 | T3_TE_0050 | SIT Operational Approach & Plan approved | - | System Design & Build | TE | - | - | - | - | SIT Operational Approach & Plan | TMAG | SI Test | -
T1 | T1_RA_0300 | Readiness Assessment 3 - Design & Build Checkpoint 1 - Complete | - | System Design & Build | RA | - | - | T1_CP_2000 Control Point 2 | - | Readiness Assessment 3 Final Report | PSG | PPC | -
T1 | T1_RE_1000 | Code changes baselined (M6) | - | System Design & Build | RE | - | Yes | - | T2_RE_0005, T2_RE_0010, T2_RE_0015, T2_RE_0020, T2_RE_0025, T2_RE_0030, T2_RE_0035, T2_RE_0040, T2_RE_0045 | - | PSG | SRO Design, Code Bodies | -
T2 | T2_RE_1005 | Smart Meters Act powers enabled (M7) | - | System Design & Build | RE | - | - | T1_CP_3000 Control Point 3 | - | - | CCAG | SRO Design | -
T3 | T3_TE_0055 | SIT Migration Approach & Plan approved | - | System Design & Build | TE | - | - | - | - | SIT Migration Approach & Plan | TMAG | SI Test | -
T3 | T3_TE_0065 | SIT Component Integration preparation (Scenarios, Data, Environments, Scripts) complete | - | System Design & Build | TE | - | - | - | T3_TE_0030 | Test Scenarios Test Data Test Scripts | TMAG | SI Test | -
T3 | T3_TE_0070 | SIT Functional preparation (Scenarios, Data, Environments, Scripts) complete | - | System Design & Build | TE | - | - | - | T3_TE_0035 | Test Scenarios Test Data Test Scripts | TMAG | SI Test | -
T3 | T3_TE_0060 | Data Service Emulators released | - | System Design & Build | TE | - | - | - | - | - | TMAG | SI DevOps | -
T3 | T3_TE_0080 | SIT Non-Functional preparation (Scenarios, Data, Environments, Scripts) complete | - | System Design & Build | TE | - | - | - | T3_TE_0045 | Test Scenarios Test Data Test Scripts | TMAG | SI Test | -
T2 | T2_TE_0085 | SIT PP Market Interfaces & Services (Metering, Data, Registration, Network Operations, UMSO) DBT complete | - | System Design & Build | TE | - | - | T1_TE_1000 SIT start (M9) | T3_TE_0010, T3_TE_0040 | - | TMAG | SI Test | -
T2 | T2_TE_0075 | Central Systems DBT complete | - | System Design & Build | TE | - | - | T1_TE_1000 SIT start (M9) | - | - | TMAG | SI Test | -
T1 | T1_TE_1000 | System Integration Testing (SIT) Start (M9) | - | System Design & Build | TE | - | Yes | - | T2_TE_0005, T2_TE_0075, T2_TE_0085, T3_TE_0065, T3_TE_0070, T3_TE_0080, T3_DE_0010, T3_DE_0015, T3_TE_1010, T3_TE_1010 | - | PSG | SI Test | -
T1 | T1_CP_2000 | Control Point 2 - Start of Integration & Test | - | System Design & Build | CP | - | Yes | - | - | Control Point 2 Report | PSG | CPT | -
T1 | T1_RA_0400 | Readiness Assessment 4 - Start of Integration & Test - Complete | - | System Design & Build | RA | - | - | T1_CP_2000 Control Point 2 | - | Readiness Assessment 4 Final Report | PSG | PPC | -
T3 | T3_TE_1005 | CSS & SMRS Simulators released | - | System Design & Build | TE | - | - | - | - | - | TMAG | SI DevOps | -
T3 | T3_DE_0010 | Design assurance of Central Systems complete | - | System Design & Build | DE | - | - | - | - | - | DAG | SI Design | -
T3 | T3_DE_0015 | Design assurance of SIT PPs complete | - | System Design & Build | DE | - | - | - | - | - | DAG | SI Design | -
T3 | T3_TE_1010 | PIT assurance of Central Systems complete | - | System Design & Build | TE | - | - | - | - | - | TMAG | SI Design | -
T3 | T3_TE_1010 | PIT assurance of SIT PPs complete | - | System Design & Build | TE | - | - | - | - | - | TMAG | SI Design | -
T2 | T2_RE_1010 | Code changes delivered (M8) | - | System Design & Build | RE | - | - | T1_CP_3000 Control Point 3 | T1_RE_1000, T2_RE_1005 | - | CCAG | SRO Design, Code Bodies | -
T2 | T2_TE_1015 | SIT Component Integration Start | - | Integration & Test | TE | - | - | T1_CP_3000 Control Point 3 | T3_TE_0030, T3_TE_0040, T3_TE_0065 | SIT Component Integration Test Readiness Report | TMAG | SI Test | -
T3 | T3_TE_1020 | Qualification Testing preparation (Scenarios, Data, Environments, Scripts) complete | - | Integration & Test | TE | - | - | - | T3_TE_0020 | Test Scenarios Test Data Test Scripts | TMAG | SI Test | -
T3 | T3_TE_1025 | SIT Operational preparation (Scenarios, Data, Environments, Scripts) complete | - | Integration & Test | TE | - | - | - | T3_TE_0050 | Test Scenarios Test Data Test Scripts | TMAG | SI Test | -
T2 | T2_TE_1030 | SIT Component Integration Complete | - | Integration & Test | TE | - | - | T1_CP_3000 Control Point 3 | T2_TE_1015 | SIT Component Integration Test Completion Report | TMAG | SI Test | -
T2 | T2_TE_1035 | SIT Functional Start | - | Integration & Test | TE | - | - | T1_CP_3000 Control Point 3 | T3_TE_0035, T3_TE_0060, T3_TE_0070 | SIT Functional Test Readiness Report | TMAG | SI Test | -
T3 | T3_TE_1040 | SIT Migration preparation (Scenarios, Data, Environments, Scripts) complete | - | Integration & Test | TE | - | - | - | T3_TE_0055 | Test Scenarios Test Data Test Scripts | TMAG | SI Test | -
T1 | T1_RA_0500 | Readiness Assessment 5 - Design & Build Checkpoint 2 - Complete | - | Integration & Test | RA | - | - | T1_CP_3000 Control Point 3 | - | Readiness Assessment 5 Final Report | PSG | PPC | -
T2 | T2_TE_1045 | SIT Non-Functional Start | - | Integration & Test | TE | - | - | T1_CP_3000 Control Point 3 | T3_TE_0040, T3_TE_0045, T3_TE_0060, T3_TE_0080 | SIT Non-Functional Test Readiness Report | TMAG | SI Test | -
T3 | T3_TE_1050 | SIT PP Sandbox Testing Start | - | Integration & Test | TE | - | - | - | - | - | TMAG | SI Test | -
T1 | T1_CP_3000 | Control Point 3 - Start of Qualification | - | Integration & Test | CP | - | Yes | - | T3_TE_0020, T3_TE_0040, T1_RE_1000, T3_TE_0060, T3_TE_1020, T2_TE_1030, T1_CP_3000, T2_TE_1055, T2_RE_0030 | Control Point 3 Report | PSG | CPT | -
T1 | T1_RA_0600 | Readiness Assessment 6 - Start of Qualification - Complete | - | Integration & Test | RA | - | - | T1_CP_3000 Control Point 3 | - | Readiness Assessment 6 Final Report | PSG | PPC | -
T2 | T2_TE_1055 | SIT Functional Complete | - | Integration & Test | TE | - | - | T1_CP_3000 Control Point 3 | T2_TE_1035 | SIT Functional Test Completion Report | TMAG | SI Test | -
T2 | T2_TE_1060 | Non-SIT PP Market Interfaces & Services (Metering, Data, Registration, Network Operations, UMSO) DBT complete | - | Integration & Test | TE | - | - | T1_CP_3000 Control Point 3 | T3_TE_0010, T3_TE_0040 | - | TMAG | SI Test | -
T3 | T3_DE_0020 | Design assurance of non-SIT PPs complete | - | Integration & Test | DE | - | - | - | - | - | DAG | SI Design | -
T3 | T3_TE_1065 | PIT assurance of non-SIT PPs complete | - | Integration & Test | TE | - | - | - | - | - | TMAG | SI Design | -
T2 | T2_TE_1070 | SIT PP Back-End Systems DBT Complete | - | Integration & Test | TE | - | - | T1_MT_1000 Start of 1 year migration for UMS/Advanced (M11) | - | - | TMAG | SI Test | -
T2 | T2_TE_1075 | SIT Migration Start | - | Qualification | TE | - | - | T1_CP_4000 Control Point 4 | T3_TE_0055, T3_TE_0060, T3_TE_1040 | SIT Migration Test Readiness Report | TMAG | SI Test | -
T2 | T2_TE_1080 | SIT Non-Functional Complete | - | Qualification | TE | - | - | T1_CP_4000 Control Point 4 | T2_TE_1045 | SIT Non-Functional Test Completion Report | TMAG | SI Test | -
T2 | T2_TE_1085 | SIT Operational Start | - | Qualification | TE | - | - | T1_CP_4000 Control Point 4 | T3_TE_0050, T3_TE_0060, T3_TE_1025 | SIT Operational Test Readiness Report | TMAG | SI Test | -
T2 | T2_TE_1090 | SIT Migration Complete | - | Qualification | TE | - | - | T1_CP_4000 Control Point 4 | T2_TE_1075 | SIT Migration Test Completion Report | TMAG | SI Test | -
T2 | T2_TE_1095 | SIT Operational Complete | - | Qualification | TE | - | - | T1_CP_4000 Control Point 4 | T2_TE_1085 | SIT Operational Test Completion Report | TMAG | SI Test | -
T2 | T2_MT_0015 | Central systems ready for migrating MPANs (M10) | - | Qualification | MT | - | - | T1_CP_4000 Control Point 4 | - | - | TMAG | CPT | -
T1 | T1_CP_4000 | Control Point 4 - Start of Migration | - | Qualification | CP | - | Yes | - | T2_TE_1080, T2_TE_1090, T2_TE_1095 | Control Point 4 Report | PSG | CPT | -
T1 | T1_RA_0700 | Readiness Assessment 7 - Start of Migration - Complete | - | Qualification | RA | - | - | T1_CP_4000 Control Point 4 | - | Readiness Assessment 7 Final Report | PSG | PPC | -
T2 | T2_TE_1100 | Non-SIT PP Back-End Systems DBT Complete | - | Qualification | TE | - | - | T1_MT_1000 Start of 1 year migration for UMS/Advanced (M11) | - | - | TMAG | SI Test | -
T1 | T1_MT_1000 | Start of 1 year migration for UMS/Advanced (M11) | - | Qualification | MT | - | Yes | - | - | - | PSG | CPT | -
T2 | T2_MT_0020 | Load Shaping Service switched on (M13) | - | Qualification | MT | - | - | - | - | - | TMAG | CPT | -
T1 | T1_RA_0800 | Readiness Assessment 8 - Ready to Accept New MPANs - Complete | - | Migration Period | RA | - | - | - | - | Readiness Assessment 8 Final Report | PSG | PPC | -
T2 | T2_TE_1105 | Qualification Test Execution complete | - | Migration Period | TE | - | - | T1_CP_5000 Control Point 5 | T1_CP_3000, T2_RE_1010 | - | TMAG | SI Test | -
T1 | T1_MT_2000 | All suppliers must be able to accept MPANs under the new TOM (one way gate) (M14) | - | Migration Period | MT | - | Yes | - | - | - | PSG | CPT | -
T2 | T2_MT_2005 | Start of 1 year migration for Smart/Non-smart (M12) | - | Migration Period | MT | - | - | T1_MT_3000 Full transition complete (M15) | - | - | TMAG | CPT | -
T1 | T1_RA_0900 | Readiness Assessment 9 - Migration Checkpoint- Complete | - | Migration Period | RA | - | - | T1_MT_3000 Full transition complete (M15) | - | Readiness Assessment 9 Final Report | PSG | PPC | -
T1 | T1_MT_3000 | Full transition complete (M15) | - | Migration Period | MT | - | Yes | - | - | - | TMAG | CPT | -
T1 | T1_CP_5000 | Control Point 5 - Cut over to new Settlement Timetable | - | Early Live Running | CP | - | Yes | - | - | Control Point 5 Report | PSG | CPT | -
T1 | T1_RA_1000 | Readiness Assessment 10 - Ready for New Settlement Timetable - Complete | - | Early Live Running | RA | - | - | T1_CP_5000 Control Point 5 | - | Readiness Assessment 10 Final Report | PSG | PPC | -
T1 | T1_MT_4000 | Cut over to new settlement timetable (M16) | - | Early Live Running | MT | - | Yes | - | - | - | PSG | CPT | -